Activity: Springing licenses

A springing license is a legal agreement whereby an author grants future permission to use the work under openly accessible terms. This license differs from the author addenda and publication agreements described above, at least as initially developed, because those agreements will enable authors to immediately publish their works under openly accessible terms. We will develop a legally sound mechanism that enables authors to establish future terms for publication under OA terms when the work is first made available under restricted-access terms. CC will partner with the Free Culture Trust and its founding members including Question Copyright and Wikimedia Foundation to develop this legal tool. Additionally, we will consult with publishers and socialize the tools during the development phase to ensure broadest global impact and acceptance.

| Timing | Description of Activity |
| --- | --- |
| Year 1 | - Identify the most viable legal mechanism for granting future copyright licenses - Vet and refine preferred legal mechanism with authors, publishers, and affiliates |
| Year 2 | - Publish a draft of the springing license incorporating the preferred legal mechanism for public comment and input from authors and publishers - Design technical requirements for and create prototype of a chooser that enables authors to apply a springing license to their works |
| Year 3 | - Finalize and publish the springing license the CC website with the chooser - Promote adoption of the springing license with authors and publishers - Promote implementation of the springing license and chooser with academic publications - Develop educational tools for authors |

Outputs

a)	What specific outputs do you expect to achieve as a result of Arcadia funding? This section should include both quantitative and qualitative results, and the timescale (i.e. short, medium or longer term). If possible, please specify the outputs you plan to attain each year.

The primary output is a suite of tools (legal and web-based software) for use in the OA publication process that maximizes the ability of authors to publish their works, whether published in the past or future, under OA terms. Qualitative outputs are described in Section 7(d) and Section 8, below.

| Funded Activity | Primary Outputs |  |  |
| --- | --- | --- | --- |
|  | Year 1 | Year 2 | Year 3 |
| Authors Addenda / Publisher Agreement | Model addendum(a) published for use by authors Educational guide to model addenda for authors published | On-line addenda engine launched Model publishing agreement published Educational guide for model publishing agreement published | Concerted outreach, socialization, and integration of both tools |
| Springing License | Complete and publish results of academic consultation mechanisms for granting future permissions | Springing license published for consultation | Springing license published Educational guide for authors published |
| Termination of Transfer / Reversionary Rights | ToT consultation and beta launched, with template reversionary rights letter | Launch U.S. ToT engine Publish model reversionary rights letter (to exercise ToT when calculator confirms right exists) Publish educational materials for authors and publishers | Publish adaptation process for ToT and reversionary rights letter in other jurisdictions Begin publishing localized versions of ToT engine and related model letters |

b)	What challenges do you expect to encounter? How do you plan to deal with them?

- Internationalization. Creating legal agreements that work globally and are easily understandable by authors and publishers worldwide is extraordinarily challenging. This is especially the case for termination of transfer tools because there is no single law that applies. Each jurisdiction has its own legal framework for how an author regains rights from publishers. We will work with our network of legal experts to write these agreements to account for different laws to maximize their use and adoption globally.

- Author resistance. Authors want to get their work published, not spend time negotiating with publishers or expending time and resources understanding their rights and how to retain or regain them. For the legal tools to be used and effective, we will need to provide easy-to-understand educational resources. CC will develop these resources in collaboration with academic organizations that understand the needs of authors, including SPARC, PLoS, and Authors Alliance.

- Resistance to adoption by hybrid OA and conventional academic publishers. All publishers have some unique dimension to their business models. Academic publishers may be generally categorized in one of three groups. Engagement with all types of publishers – OA only, hybrid OA-conventional, and conventional only – will be essential during the consultation pre-launch phases of the legal tools development, and after during the adoption stage. We expect authors to experience the most resistance when using our tools from the hybrid OA and conventional publishers, because our model will push for change to some dimension of their existing models. We will use our established relationships with several publishers and publishing associations, including Nature Publishing Group and the International Association of Scientific, Technical, and Medical Publishers (which sought to create new “open access” licenses for use by its members) throughout the process. Additionally, we will rely on the relationships established by organizations such as PLoS, SPARC, and Authors Alliance.

- Anticipating changes in OA ecosystem; license proliferation. Some hybrid and conventional academic publishers believe their business models are being threatened as they work to respond to an increase in the number in OA-mandated policies by governments and universities. There is also an increase in the number of custom licenses and policies that are promoted by publishers as alternatives to CC’s standard licenses, as suggested above in point 3. This proliferation creates confusion for authors and undermines the goals of governments that promote adoption of CC standard licenses. Similarly, it is difficult to anticipate changes in government policies that mandate OA publishing practices. When developing these new tools, CC will listen carefully for these concerns and changes, and will respond where important through outreach and publication of articles.

c)	Arcadia supports open access to research findings. We expect authors of research conducted through our funds to make their results available for free via a stable Internet depository . Please tell us what research and other materials you will produce, and how they will be made accessible.

All final work products developed using Arcadia funding will be made available under a Creative Commons Attribution 4.0 International license or, in the case of data and the text of legal tools, under the CC0 Public Domain Dedication. All work products will be made available under those terms to the public on the Creative Commons website.

7. Outcomes; implementation strategy and adoption plan

d)	What kinds of outcomes do you hope for? How will your particular outputs address the problem you have set out to solve?

Outcomes

Creative Commons hopes for two primary outcomes as a result of producing the legal agreements and tools described in this proposal. The first is meaningful growth in quantity and quality of content that is shared consistent with OA principles, and the second is the number of authors and publishers embracing OA as the preferred model for sharing academic research and scholarship.

At present, authors have no standard and easy-to-use tools to retain or regain their right to make their works openly accessible under OA terms. For those who have already assigned their publication rights to a publisher under conventional, restricted-access terms, the termination of transfer rules in the United States and elsewhere are extraordinarily complex. Navigating the legal intricacies to arrive at a conclusion that their claim to regain rights is well founded presents challenges. Among others, there is a high transaction cost in the form of legal fees that many authors cannot bear in order to figure out if they can exercise their reversionary right.

For those wishing to retain or preserve the option in the future to make their new works openly accessible, their choices are similarly limited: they may publish on their own and forego possibly more optimal marketing and distribution mechanisms that conventional publishers may provide, or surrender their right to make their works openly accessible in the future to take advantage of promised marketing and distribution impact convention publishers offer. Once published, the legal agreements and tools to be developed will empower authors to take back their rights or secure their rights in the future so they can publish under OA terms.

We also expect an increase in understanding and collaboration between authors and publishers. This includes respect between authors and publishers for each other’s challenges and publication objectives, and identification of concrete and mutually beneficial ways to attain their respective goals. All of the activities described will involve open communications and transparent development of tools that are designed to be win-win for authors, publishers, and the greater public. These tools will reduce fear, uncertainty and scepticism for authors, publishers, and the public about the value of OA publishing and the reusability of works.

Implementation Strategy and Adoption Plan

CC will maximize the impact and adoption of these new legal agreements and tools through focused, early, and frequent engagement with those who will benefit from the solutions provided and who will use the tools throughout the development process. We will collaborate with other organizations representing authors and publishers (both hybrid and conventional) to amplify the benefits of adoption, and to provide educational and technology solutions that complement the new tools and make them easy to understand and use.

- Collaborative engagement: A key to ensuring new CC legal tools achieve their fullest potential for adoption is to engage early and frequently in the development process with those seeking a solution to challenges associated with OA publishing, and with those who are expected to use these new legal tools. This collaboration allows us to thoroughly understand the problem to be resolved, and also to devise the most effective solution. This approach has the added benefit of cultivating a group of early adopters that have an investment in the new tools created. These early adopters will serve as models for others. As noted above under Activities, CC plans collaborative engagements with authors and publishers throughout the development of all of legal agreements and tools described here. In every instance, we will be closely connected to those with an investment in the long-term success of OA, and build bridges where possible with those who are reluctant.

- Publish and solicit focused input on drafts and prototypes to ensure international operation: Similarly, we will follow our standard processes to publish early drafts and prototypes for public comment. As we publish, we will solicit specific feedback from authors, publishers, and international legal experts who understand the complexities of creating robust legal agreements and tools. We will incorporate this feedback to create well-accepted, sound legal tools for use worldwide.

- Technology and educational support for new tools. To be successful, OA publishing requires seamless integration of licensing and supporting legal agreements and tools in the natural workflow of authors and publishers. Each of the legal agreements and tools described will involve development of a corresponding technology solution and educational materials that will make them easy for authors and publishers to embrace.

- Promote and engage. CC is an active, engaged, and respected leader in a variety of open movements, including the OA movement, with a large influence and reach -- over 33,000 individuals and supporters on our mailing list, nearly 1 million subscribers on social media, and over 3.8 million monthly visits to our website. We will activate our communications channels and networks to promote these tools in various communities and to key audiences that will benefit from them.

Impact

What kinds of impact do you hope to make as a result of Arcadia funding? How will your work contribute to a broader cultural or environmental context?

The principles of OA are simple, but even with the CC license suite, there are additional details that remain complicated. If we want authors to share, we have to make it easier, and arm them tools that help them negotiate with publishers and when publishing and sharing their work.

- Authors have historically been limited in their ability to insist on how their works are published and under what terms, even in an age where self-publishing has been possible thanks to the internet. Providing tools and education for creators so that they can retain rights to publish consistent with their ethics and objectives, to reacquire rights that they have relinquished to do the same, and to proactively take steps to ensure their works will eventually be under terms that enable their broad dissemination are all goals that have not yet been achieved.

- Increasing the dominance of OA publishing as an alternative to conventional publishing models (i.e., restricted access and publisher-held copyright), which not only allows but embraces an author’s right and freedom to choose how and where their works are published and shared, with the full support of those who fund and support them (universities, foundations, governments, and colleagues).

We can liberate a large amount of scholarship that is currently locked up with publishers who control all rights but are either publishing under restricted-access terms only or are not actively promoting or distributing the works at all. Empowering authors to free their content expands the commons with more OA content that can be reused to drive innovation and discovery. This can only be accomplished if authors are aware and then have the simple, universal tools to retain their rights (author addenda and model publishing agreement), to regain their rights (reversionary ToT and model letters demanding that return of rights), and to insist publishers to grant more reuse rights in the future (the springing license).

Resources

f)	Budget. Provide a budget for your proposal with a breakdown of what our grant would be spent on, showing how the expenditure relates to the aims and objectives of the project.

Meeting expenses (budget note 3).

Securing the early participation, input, and investment of the authors and publishers expected to adopt the legal agreements and other tools under development is critical in year 1. The most efficient and effective forum to do so is the CC Global Summit (October 2015, Seoul), where CC staff, legal experts from our global affiliate network, and others seeking solutions to challenges associated with OA publishing will gather. The Global Summit is an unparalleled opportunity to garner early input on the legal tools we seek to develop from an array of experts, and to securing their investment in the future success of the. The Budget Proposal seeks de minimus funding to defray costs associated with travel by two leading outside OA experts who would not otherwise have funding to travel (e.g., representatives from Authors Alliance, SPARC, Free Culture Trust, and/or an academic publisher).

For more detail about the importance of early vetting to the successful implementation and adoption of new tools, please see Section 7 above (Implementation and Adoption Plan).

For multi-year grants, in addition to next year’s budget, please tell us how your costs would evolve from year to year, and how you plan to spread the grant money over its duration. You can update the budget each year if you need to. We pay grant instalments when we have a satisfactory report for the previous year.

Our costs will progressively decrease over the course of the 3-year grant period, with the most significant expenditures in years 1 and 2, and lower expenditures in year 3. This budget plan maximizes our opportunity to efficiently engage with a large number of stakeholders as well as the legal experts in our international affiliate network at the CC Global Summit taking place in October 2015, and to take advantage of complementary work being undertaken by like-minded organizations such as Authors Alliance and SPARC.

To maximize opportunities at the Summit taking place in October 2015 we will dedicate a proportionately greater amount of resources to the activities described in year 1. The budget proposed does not fund the summit, but allows us to accelerate our work in the early phase to be opportunistic about the concentration of CC affiliates. Arcadia resources will be used to develop prototypes and models that can be vetted with affiliates and stakeholders at the event, to ensure that the most relevant and impactful stakeholders lend their expertise, and then to maximize momentum gained there to efficiently advance the tool development, collect comments, and advance the publication processes thereafter. We expect year 3 costs to be slightly lower than year 1 and 2, when our focus turns to education and outreach.

If you are requesting core funding, provide a budget for your operational expenses, as well as, broadly, the main expenditures on your major projects.

CC is not seeking core funding. All of the activities and outputs relate to new projects undertaken as a consequence of this funding.

If your expenses will be co-funded, please provide figures for the amounts to be spent from the Arcadia grant and for the total cost.

At present, all expenses are exclusively funded by Arcadia, although shortfalls will be covered out of CC’s general operating budget. See response to (i) below for our future funding plans.

What other donations or sources of funding will you use to meet your budget? Please describe the timeline, size and purpose of your existing or expected grants.

In the short term, CC will use separate general operating support to complement the funding from Arcadia. Once early outputs have been developed for discussion at the Global Summit in October 2015, CC intends to search and secure additional funding with successes and proof-of-concepts in hand.